## Sheet1
ID | Name | Likelihood | Impact | Control Mechanisms
1 | Improper Time Management | med/low | high | Follow the Gannt chart
2 | HDD/storage failure | low | high | All work will be backed up to github
3 | Illness/Injury | med | med | Should the need arise I will apply for an extention to the due date.
4 | RSI (repetetive strain injury) | med | low | Work with proper posture and set up workstation properly. And take frequent breaks
5 | Eye strain | med | low | Ensure room is well lit when working on a screen.
6 | Incorrect Task Prioritisation | med | med | Iteratively re-asses the work being done and compare it to the mark scheme.
7 | Postural problems | med | low | Work with proper posture and set up workstation properly. And take frequent breaks